## Slide 1
PEER | CSSR | INDIA
PPT 2 -
SOP ON CSSR
Presented By:- Kamlesh Dhoundiyal,2IC

## Slide 2
Collapse Structure Search & Rescue is a term applied to rescue & recovery operations at the scene of a structural collapse or multiple structural collapse.
A collapse refers to a failure of a structure .
INTRODUCTION

## Slide 3
CSSR is an operation to conduct safe and effective search & rescue operation in which a wide range of knowledge, skill & ability are required with use of advance techniques to locate, extricate & stabilize the victim trapped inside the confined space/void of a collapsed structure.
The ultimate goal of search & rescue operation is to rescue trapped victims in shortest span of time.
INTRODUCTION

## Slide 4: The aim of this SOP is to lay down guidelines for NDRF teams for responding in CSSR operations.
AIM

## Slide 5
The purpose of this SOP is to establish the procedure for the response of the Search and Rescue Teams of NDRF BN for Collapsed Structure.
The SOP provides guidance and assign responsibility for adopting various executive actions to ensure prompt response during CSSR operation
PURPOSE

## Slide 6
To define a ‘Standard Operating Procedure’ for CSSR operation.
The SOP applies to all elements of the Command while performing CSSR operations.
This SOP is a guideline and should be reviewed periodically.
SCOPE

## Slide 7
The objective of this SOP is to formulate action plan for specialist response during a CSSR Operation while all safety measures are to be followed. These are as under:
Guidelines for rescuers during CSSR operation.
Reducing reaction time of the teams in responding to the CSSR operation.
OBJECTIVES
Upon Completion of this lesson, you will be able to:

## Slide 8
Coordinated and collaborative instructions during CSSR Operation.
Achievement of best result by well-planned rescue operation.
Establishment of BoO, CP, Communication Post, Medical Post, Staging Area based on INSARAG Guidelines & Methodology.
OBJECTIVES
Upon Completion of this lesson, you will be able to:

## Slide 9
To take immediate actions for temporary support and protection to collapsed structures.
To rescue the survivors trapped under the debris from the damaged/ collapsed structure.
To provide First Aid to the trapped victims and to dispatch them for advance medical care.
To recover, hand-over and dispose off the bodies of the deceased.
OBJECTIVES
Upon Completion of this lesson, you will be able to:

## Slide 10
On receipt of information regarding any structural collapse, one version of information be available with all Supervisory Officers i.e. battalion Commandant, DC (Ops), Unit Control Room and Team Commander.
ROLE OF SUPERVISORY OFFICERS

## Slide 11
On getting the information, DC (Ops) of the unit will immediately alert the ‘On wheel’ team for getting ready for move and unit Control Room to get the details about the operation from the incident site.
He will also inform the Commandant and DC (Ops) at HQ NDRF.
THE DC (OPS) OF THE UNIT WILL BE RESPONSIBLE FOR:

## Slide 12
Simultaneously, coordinate with district officials (DM/ADM/SP/SDMA or any other local officials) for actual details of the team to augment(increase amount) the ‘On wheel’ team before move.
To brief the team before move and check the availability of TEAs as per the requirement.
THE DC (OPS) OF THE UNIT WILL BE RESPONSIBLE FOR:

## Slide 13
To remain in contact with the local authorities/media for further updates and trace the requirements of additional teams/resources, if any.
To remain in constant touch with the team commander and guide him during the operation.
Sharing of all operational details to HQ NDRF along with good quality photo and videos. All above action be closely monitored and supervise by the Commandant.
THE DC (OPS) OF THE UNIT WILL BE RESPONSIBLE FOR:

## Slide 14
Unit Control Room play a very vital role. It acts as a buffer between the team and Bn. Commanders/HQ NDRF Control Room:
Provide all the operational details such as road maps, civil officials contact details, logistics details, current situation, stake holders on ground etc. to the SAR team commander moving out for the CSSR Operation.
Receive all the information related to Incident/Operation, consolidate and share it with higher Headquarter.
ROLE AND TASK OF UNIT CONTROL ROOM

## Slide 15
Upgrade the information about the incident and will share with team commander.
Collect the photos & videos of Incident/Operation and share it with higher Headquarter.
Maintain a data bank of the information, photos and videos for de-briefing, case studies and future requirements.
Collect en-route information from Team Commander.
ROLE AND TASK OF UNIT CONTROL ROOM

## Slide 16
Collect the information regarding initial assessment of the incident.
Remain in close contact with Team Commander.
Collect the information of on-going operation and outcomes.
Collect and consolidate the Incident Report of the operation and send it to HQ NDRF as per proforma.
ROLE AND TASK OF UNIT CONTROL ROOM

## Slide 17
It will be the responsibility of team Commander of CSSR team who is involved in the CSSR Operation to ensure that all aspects of this SOP must be adhered. On receipt of warning orders, Team commander will ensure the following-
Collect all concerned information about incident from DC (Ops)/ Unit Control Room and will plan his strategy as per ground conditions of the concerned State/ District.
ROLE AND TASK OF TEAM COMMANDER

## Slide 18
Chalk out the shortest route to be followed by the vehicles during the movement and discuss it with the DC (Ops)
Detail a suitable person to carry camera and recording equipment with spare battery.
Availability of CSSR equipment, Squad, Communication equipment and emergency medicines with the team.
ROLE AND TASK OF TEAM COMMANDER

## Slide 19
On the way to the incident site, he will collect the required information from local sources/media and liaise with local administration for essential requirements and ask for a guide
Upgrade the information from local administration, Unit Control Room, media and other stake holders.
On arrival at incident site, team commander will assess the situation and plan the employability of his team accordingly for prompt response.
ROLE AND TASK OF TEAM COMMANDER

## Slide 20
Brief Sub-team commanders and team members to familiarize them with their area of operation. He will also brief them about the safety instructions, local customs and culture.
After assessment and initial briefing, he will start the rescue operation with all their Search and Rescue TEA, victim locating instruments etc. Search and Rescue operation will be conducted as per INSARAG guidelines.
Ensure efficient and multiple communication means like HF/VHF/QDA/Sat Phone with Unit HQ, HQ NDRF, SEOC and DEOC.
ROLE AND TASK OF TEAM COMMANDER

## Slide 21
Ensure that all electric and gas connections are cut off and the building is safe to enter.
Liaise with the other agencies working in the area for better co-ordination during the rescue operation
Physically monitor the operation and record the outcomes
Maintains seamless communication with Control Room of the unit with all the progress related to CSSR Ops.
ROLE AND TASK OF TEAM COMMANDER

## Slide 22
Brief the Incident Commander on the progress of the operation and discuss the further planning of the operation.
Ensure the rest, Adm. arrangements of his team.
Ensure that all sub-teams remain in contact with team commander for better span of control.
To ensure that rescuers do not enter any building that is damaged unless it has been properly checked and declared “GO” by the safety officer.
ROLE AND TASK OF TEAM COMMANDER

## Slide 23
To ensure the rescue operation should be conducted in presence of civil authority or the representative appointed by them to avoid any legal complications.
To ensure good quality photographs & videos of operational activities and will send the same to unit Control Room at a regular interval.
ROLE AND TASK OF TEAM COMMANDER

## Slide 24
Team commander will not get himself engaged unnecessarily with electronic & print media and no ambiguous or partial statement will be given by him during the operation.
If RO/IC is not present at incident site, then team commander may communicate with the media but will limit himself to the operational activities by his team only.
ROLE AND TASK OF TEAM COMMANDER

## Slide 25
He will assist the team commander and ensure the following:-
Responsible for proper unloading of TEAs and establishment of BoO on arrival of team at safer place.
Monitor the operation carried out by the team.
Ensure that all the rescue operation is conducted in a planned manner, as discussed.
ROLE AND TASK OF TEAM 2IC

## Slide 26
Ensure proper rest and relief for the rescuers.
Ensure adequate lighting on work site.
Team 2IC will perform the duties of Team Commander in his absence
ROLE AND TASK OF TEAM 2IC

## Slide 27
ROLE AND TASK OF SAFETY OFFICER
Responsible for operational worthiness (deservingness) of TEAs, loading of shoring materials and equipment.
Responsible for performing Structural triage and render his technical expertise regarding behaviour of collapsed structure as and when required.
Mark the entry and exit route for access and extrication.
Ensure that safety and security considerations are included in action plan and briefing.

## Slide 28
Safety officer will brief the well-established warning system and evacuation plan. He will further ensure that it must be properly briefed and executed on ground during any emergency.
Safety officer will brief about the field signals, whistle signals or any other signals by using loudhailer before start of CSSR operation.
Ensure that team is working with proper PPE on the site.
ROLE AND TASK OF SAFETY OFFICER

## Slide 29
Ensure that team personnel do not work alone and in isolation. He will ensure the buddy system during SAR.
Ensure biomedical control measures are adhered to i.e. body recovery, patient handling, sanitation & hygiene etc.
Ensure that personnel and equipment decontamination practices are followed prior to leaving the work site.
ROLE AND TASK OF SAFETY OFFICER

## Slide 30
Ensure that all team personnel are in contact with means of communications during the operation.
Safety officer will ensure rest, rotation and hydration of team members.
Maintains his position so that he is visible to all commanders present at work site during operation.
ROLE AND TASK OF SAFETY OFFICER

## Slide 31
To remain in contact with Team commander and safety officer.
To receive work instructions from team commander.
To assign task to rescuers.
To decide which specific TEA is to be used.
ROLE AND TASK OF SUB-TEAM COMMANDER

## Slide 32
To monitor work rotation of rescuers and equipment.
To update the CP on progress & task completed.
To ensure safety of his sub-team.
To maintain a log of all events, actions & expenditures
ROLE AND TASK OF SUB-TEAM COMMANDER

## Slide 33
It will be the responsibility of all the responders to know, understand and follow the directions of the SOP .
Wear proper PPE.
Carry out rescue work according to the instructions from sub-team commander.
Take proper safety measures while using TEAs.
ROLE AND TASK OF RESCUER

## Slide 34
Inform the progress of task to sub-team commander.
Request Sub-team commander for additional resources for completing task, if required.
Rescuer working as a logistic position will provide additional TEAs and other resources, if required.
Work in pairs to provide physical support, monitoring safety & rest of his buddy
ROLE AND TASK OF RESCUER

## Slide 35
Receive Adm. related instructions from the Team Commander/Team 2IC.
Ensure all Adm. arrangements for rescuers.
Ensure to provide food and water timely to the rescuers.
Ensure the safety and security of the Adm. Base.
Ensure the replenishment (renewable) of fuel, gasoline, tools and accessories.
ROLE AND TASK OF ADM NCO

## Slide 36
To provide medical support to the SAR team during CSSR operation.
Medical team will consist of one medical officer and two para-medics or as per the requirement/gravity of the incident.
To carry all emergency medicines.
ROLE AND TASK OF ADM NCO

## Slide 37
Ensure the availability of Ambulance equipped with BLS.
Ascertain the details of hospitals/ medical facilities near the incident site.
Medical officer will liaise with doctors of nearby hospitals for advance medical care
ROLE AND TASK OF MEDICAL TEAM

## Slide 38
SAR Team of NDRF will be mobilized:
On receiving specific orders from HQ NDRF.
On the request/requisition of the affected State/UT Govt./local administration or the affected authorities.
On the orders of Battalion Commandant
DECISION FOR DEPLOYMENT OF CSSR TEAM

## Slide 39
EXECUTION OF CSSR OPERATION
Phase –I: Preparation
Following preparation level is expected from all the Battalions of the NDRF at any given time for launching CSSR operation:-
Two SAR teams at BN HQ and one team at each RRC should be “On Wheel” with all the required equipment, tools and stores. On Wheel team will move within 30 minutes from the Unit/RRC location for the incident site.

## Slide 40
PHASE–I: PREPARATION
The man management and logistics management of every coy of each Battalion should be such that after taking into consideration the leave/reserve/temporary duty, three teams of each coy should be readily available for responding to any incident.
Each SAR team should comprise of all components of team as per authorization. The composition of NDRF SAR team is given as Appendix-H. However the team composition may vary keeping in view the nature/gravity of the incident and other administrative issues.

## Slide 41
PHASE –I: PREPARATION
The man management and logistics management of every coy of each Battalion should be such that after taking into consideration the leave/reserve/temporary duty, three teams of each coy should be readily available for responding to any incident.
Each SAR team should comprise of all components of team as per authorization. The composition of NDRF SAR team is given as Appendix-H. However the team composition may vary keeping in view the nature/gravity of the incident and other administrative issues.

## Slide 42
PHASE –I: PREPARATION
Before mobilization, Control Room of the Unit will provide all the available operational details such as road maps, civil officials contact details, logistic details etc. to the SAR team(s) moving out for the CSSR Operation.
Each SAR team will carry sufficient ration before leaving the campus for duration of minimum 15 days and MRE may be taken for first 48 hours by each team.
Sufficient advance for the fresh/dry ration for the team will be provided by the Unit Quarter Master.

## Slide 43
PHASE –I: PREPARATION
All Tools, Equipment and Accessories should be operationally ready through regular inspection for effective response.
The vehicles of the Unit will be earmarked for each team. Beacon lights, emergency sirens and NDRF monogram in every vehicle are mandatory. Vehicles should be operational-worthy at any time.
Mobile kennels for dogs should be available with each SAR Team.

## Slide 44
PHASE –I: PREPARATION
An ambulance equipped with BLS equipment, DM medicines along with other required stores should be prepared to be taken with SAR Team or made available at the site in coordination with the State/local authority.
Complete Communication stores with QDA & Satellite Phone should be earmarked and taken with each SAR Team.

## Slide 45
PHASE–II: ACTIVATION AND MOBILISATION
After receiving the information from the authenticated source, this phase activates. The sequence of action are as under:-
The BN Commandant will activate SAR team(s) on receipt of orders from HQ NDRF. The number of SAR Team(s) to be sent will be decided by the HQ NDRF/BN.

## Slide 46
PHASE–II: ACTIVATION AND MOBILISATION
Following information will be passed by unit Control Room to SAR team for further course of planning and action for CSSR operation:
Place of incident.
Time of incident.
Number of people affected.
Number of casualties, if any.
Other rescue agencies operating.
Number of rescue teams required.

## Slide 47
Nodal officer and his contact number.
Weather at incident site.
Hazardous materials present at incident site.
Routes/Terrain.
Action taken by local administration before arrival of SAR team.
Location of reporting of SAR teams.
Movement order along with the complete list of stores will be ready with intimation to HQ NDRF.
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 48
Briefing of SAR team will be done by the Supervisory officer/respective Team Commanders on following aspects:
Cross checking and confirming the readiness of the team on all aspects.
Details of incident site and current situation.
Route to reach the incident site.
Initial deployment plan.
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 49
Safety precautions to be taken en-route.
Briefing of drivers and halting points.
Order of March.
Checking of morale of team members and motivational briefing.
Ensuring TEAs, communication equipment, camera & other stores.
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 50
Contingency amount.
Do’s and Don’ts.
The bag and baggage to be carried by rescuers depending on topography of that place.
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 51
In this stage, SAR Team(s) and other operational elements moves from BN HQ/ RRC to incident site for conducting rescue operation.
To ensure the effective and timely response upon confirmation of the request for assistance. The Commandant/ DC (ops) of the local Unit will coordinate with the affected State/UT/District for immediate response.
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 52
PHASE–II: ACTIVATION AND MOBILISATION
Following instructions will be adhered during mobilization:-
“On Wheel” Team will be mobilised within 30 minutes after getting formal orders from HQ NDRF/BN Commandant along with its all components.
Light vehicle -1 and Medium/Heavy vehicle -3 (including one bus) will be provided to one SAR Team.

## Slide 53
Team Information Sheet will be made available with each SAR team. Unit must send this in advance to the requisitioning authority for arrangements of logistics at the incident site. This is an necesary requirement if the team is to be sent to any other country for responding in CSSR operation.
Battalion will send a message in detail regarding mobilization of SAR Team(s) mentioning its composition to the HQ NDRF.
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 54
Unit Control Room will communicate with the team en-route regarding road condition, other sister agencies working on the site, place of reporting of team and availability of resources at the site.
Decision for reinforcement lies with HQ NDRF/ BN which will be communicated immediately for further course of action.
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 55
In case of reinforcement of CSSR teams by air or rail, suitable transport as well as guide will be provided by the State/UT Govt.
For timely arrival at the disaster site. The co-ordination will be done in advance by the HQ NDRF/Concerned Battalion
PHASE–II: ACTIVATION AND MOBILISATION

## Slide 56
PHASE –III: OPERATIONS
On arrival at the operation site team will establish its Base of Operation close to the incident site keeping in view the situation on ground.
Immediately, on arrival of SAR team, Team commander will get the briefing from the Responsible Officer or appropriate designated authority, which should include all the aspects relevant for effective response by the team.

## Slide 57
PHASE –III: OPERATIONS
By the time Team Commander is taking briefing, Team 2IC and other Supervisory staff to have a look of the incident site for possibility of multiple entry/worksite.
After discussing the situation with the Responsible Officer or appropriate authority, Team Commander in consultation with Team 2IC will chalk out his action plan and execute it professionally.

## Slide 58
In case of multi storey or major building collapse, multiple entries to the building will prove fruitful. In such a case, Team Commander and Safety Officer to ensure that action of one sub team does not compromise the security of other sub teams.
The primary task of the CSSR team is to ensure the search, rescue, safety and protection of the victims trapped or entangled in any life threatening situation. Responders will triage and provide pre-hospital treatment to the injured victims before handing them over to EMS.
PHASE –III: OPERATIONS

## Slide 59
PHASE –III: OPERATIONS
In case any live victim is located, the medical component must accompany the
sub team while rescue.
During the operation by SAR team, local Govt. can be asked for all necessary services/facilities like heavy machinery (Excavators, Tractors, Bulldozers and Cranes etc.) and POL etc.

## Slide 60
Following instructions will be adhered in the operational stage of CSSR operation:-
Battalion will be in communication with the team(s) on regular basis, monitor the progress of the operation, outcomes and tasks yet to be accomplished.
Battalion will assess requirement of additional manpower & resources and will provide reinforcement to the deployed team(s).
PHASE –III: OPERATIONS

## Slide 61
Battalion will provide assistance to the team(s) in case of any difficulty and liaise with other agencies, EOC of the concerned State/ District for better co-ordination during rescue operation.
The SAR Team Commanders will brief and interact with the media as per procedure, if required.
The Unit Commandant will keep on boosting the morale of the rescuers on every achievement
PHASE –III: OPERATIONS

## Slide 62
Phase –iii: Operations
Rest and relief within the team will be ensured by team commander during the operation.
SAR Team will adhere the INSARAG guidelines and procedures during the operation. Proper coordination with other stakeholders will be ensured by team commander.

## Slide 63
SAFETY MEASURES DURING CSSR OPERATION
Incident Site:
Personal Protective Equipment:
Hygiene:
Safety Officer:
Team Safety:
Safety Violations:
It is the resoponsibility of the team commander and safety officer that safety measures are be followed by all team members during the CSSR operation.

## Slide 64
SAFETY MEASURES DURING CSSR OPERATION
Whistle Signals:
Safety Zone:
Emergency Medical Services:
Fire Extinguisher:
Maintenance:
Rotations:
Trash:
Safety Marking:
Miscellaneous:

## Slide 65
Stage – i : Securing The Scene
Stage – ii : Initial Assessment
Stage – iii : Search And Locate
Stage – iv : Gaining Access
Stage – v : Extrication Of Victim
SAFETY MEASURES DURING CSSR OPERATION

## Slide 66
PHASE–IV: DE-ACTIVATION AND DE-MOBILIZATION
After completion of operation, SAR Teams are de-mobilized:
Once the SAR team has completed the task, the decision to terminate the operation will be taken by the HQ NDRF /DIG (Ops)/Unit Commandant in consultation with the concerned State/District authority.
All required clearances are taken from the concerned State/District authorities.

## Slide 67
PHASE–IV: DE-ACTIVATION AND DE-MOBILIZATION
Before de-mobilization of SAR team, De-mobilization Form will be prepared by team commander.
Check and count all equipment at ops site for loss and damage, if any. Stores are loaded and teams move back to their respective locations.

## Slide 68
Following instructions should be adhered during the de-mobilization stage: -
After the operation is finished, Unit Commandant will demobilize all the teams as per the planning. The teams which were inducted first should be de-inducted first and the teams which were inducted in the last should be de-inducted in the last. Unit Control Room will inform HQ NDRF about the progress of de-mobilization.
PHASE–IV: DE-ACTIVATION AND DE-MOBILIZATION

## Slide 69
PHASE–IV: DE-ACTIVATION AND DE-MOBILIZATION
Unit Control Room will assist the teams in smooth withdrawal from operation site.
Unit Control Room will inform the HQ NDRF regarding the arrival of the teams

## Slide 70
PHSE–V: POST-OPERATIONAL ACTIVITIES
After arrival of teams at BN HQ, following post-operational activities are carried out:
Checking of all TEAs will be done by unit ‘MOST’.
Loss & damage of any TEA will be brought in the notice of unit HQ.
Medical and physical examination of all rescuers will be ensured.
PTSD session for all rescuers will be organized at BN HQ.

## Slide 71
PHASE–V: POST-OPERATIONAL ACTIVITIES
De-briefing session will be conducted on following aspects:-
Summary of all activities.
Operational achievements.
Improvisations and innovations made, if any.
Problems faced during the operation
Mis-happening, if any, during the entire operation.

## Slide 72
PHASE–V: POST-OPERATIONAL ACTIVITIES
Requirement of TEAs or any other special equipment.
Adm. and logistic arrangements.
Points for improvement.
Lessons learnt during the operation.
Feedback report.

## Slide 73
PHASE–V: POST-OPERATIONAL ACTIVITIES
Detailed report/Post-Ops Report will be sent to HQ NDRF as per the proforma mentioned at Appendix-T.
Case study.
Data ban

## Slide 74
ADMINISTRATION AND LOGISTIC ARRANGEMENTS
Following administrative and logistics arrangement will be ensured by the responding Battalions:
Contingency Amount: Each SAR team should take following amount:
Rs. 10,000/- for unforeseen expenses
Rs. 30,000/- for fresh purchase
Rs. 10,000/- for MT

## Slide 75
ADMINISTRATION AND LOGISTIC ARRANGEMENTS
By Rail: As per requirement of SAR team:
One coach per team.
One SLR coach for two teams.
By Air: As per requirement of SAR team(s).
Note:- Packing and load table should be prepared in advance.

## Slide 76
Adm. Stores: Adm. Stores including utensils to be carried by a SAR team are mentioned as Appendix- E.
Weapons for Security: Weapons which are required to be carried by a SAR team are mentioned as Appendix- F.
Personal Belongings of Responders: The personal belongings which are required to be carried by the members of the SAR team are mentioned as Appendix-G
ADMINISTRATION AND LOGISTIC ARRANGEMENTS

## Slide 77: REVIEW
The objective of this SOP is to formulate action plan for specialist response during a CSSR Operation while all safety measures are to be followed. These are as under:
Guidelines for rescuers during CSSR operation.
Reducing reaction time of the teams in responding to the CSSR operation.

## Slide 78: REVIEW
Coordinated and collaborative instructions during CSSR Operation.
Achievement of best result by well-planned rescue operation.
Establishment of BoO, CP, Communication Post, Medical Post, Staging Area based on INSARAG Guidelines & Methodology.

## Slide 79: REVIEW
To take immediate actions for temporary support and protection to collapsed structures.
To rescue the survivors trapped under the debris from the damaged/ collapsed structure.
To provide First Aid to the trapped victims and to dispatch them for advance medical care.
To recover, hand-over and dispose off the bodies of the deceased.

## Slide 80
This SOP has been prepared with the objective that all the required and correct procedures in CSSR operation should be adopted so that the entire task is completed in prescribed schedule.
This SOP also aims at fixation of accountability at each stage.
This SOP should be reviewed as and when the procedures and guidelines mentioned here become obsolete with time and as the situation demands.
CONCLUSION:

## Slide 81
THE SOP IS NOT INTENDED TO BE EXHAUSTIVE/FINAL AND IS SUBJECT TO MODIFICATION FROM TIME TO TIME AS PER THE REQUIREMENT/EXIGENCIES
DISCLAIMER

## Slide 82
ANY QUESTIONS ?

## Slide 83
THANK YOU